## Sheet1
No. | Date | Activity | Weather | Labor | Project Size | Planned Days | Supply Chain | Risk Mitigation | Delay
1 | Jan | Foundations | Rain | 0.95 | Large | 14 | Normal | Soil stabilization | 4
2 | Jan | Concrete Pouring | Clear/Cold | 1 | Mega | 20 | Pump Failure | Backup pump on-site | 2
3 | Feb | Steel Structure | High Winds | 0.8 | Infrastructure | 45 | Steel Shortage | Early procurement | 9
4 | Feb | Electrical (Main) | Clear | 0.9 | Giga | 60 | Transformer Delay | Temporary generators | 15
5 | Mar | Exterior Facades | Sandstorm | 0.7 | Large | 30 | Glass Breakage | Specialized storage | 6
6 | Mar | HVAC Ducting | Dust | 0.85 | Mega | 25 | Design Clash (BIM) | BIM Coordination | 5
7 | Apr | Interior Plaster | Clear | 1 | Medium | 15 | Normal | Accelerated drying | 0
8 | Apr | Elevator Shafts | Clear | 1 | Large | 40 | Customs Delay | Early shipping | 12
9 | May | Roof Waterproofing | High Heat | 0.9 | Medium | 10 | Normal | Night shift work | 3
10 | May | Infrastructure Pipes | Clear | 0.95 | Infrastructure | 90 | Underground Utility | Utility mapping | 10
11 | Jun | Slab Casting | Extreme Heat | 0.8 | Giga | 20 | Normal | Chilled water mix | 4
12 | Jun | External Cladding | Extreme Heat | 0.75 | Large | 25 | Supply Shortage | Local sourcing | 7
13 | Jul | Landscape/Trees | Extreme Heat | 0.85 | Mega | 30 | Plant Mortality | Automated irrigation | 8
14 | Jul | Road Paving | Extreme Heat | 0.7 | Infrastructure | 15 | Asphalt Delay | Batch plant priority | 5
15 | Aug | Final Finishing | High Heat | 0.9 | Small | 20 | Normal | Air-conditioned site | 0
16 | Sep | Fire Fighting Sys | Clear | 1 | Large | 25 | Valve Shortage | Pre-ordering valves | 4
17 | Sep | Smart Home Hub | Dust | 0.95 | Medium | 10 | Firmware Issue | Remote tech support | 3
18 | Oct | Swimming Pools | Light Rain | 0.9 | Large | 30 | Normal | Water testing | 2
19 | Oct | Main Substation | Clear | 1 | Giga | 120 | SEC Approval | Gov Liaison Officer | 20
20 | Nov | Excavation | Heavy Rain | 1 | Large | 15 | Muddy Terrain | Gravel access roads | 7
21 | Dec | Smart Systems | Clear | 1 | Mega | 15 | Tech Setup Issue | Early software testing | 7
22 | Dec | Final Inspection | Clear | 1 | Medium | 10 | Compliance Issue | Pre-audit check | 12
23 | Jan | Soil Compaction | Rain | 0.85 | Infrastructure | 20 | Normal | Soil stabilization | 6
24 | Jan | Concrete Curing | Cold | 0.95 | Large | 7 | Additive Delay | Accelerated curing agents | 3
25 | Feb | Tower Crane Ops | High Winds | 0.7 | Giga | 120 | Safety Protocol | Wind speed sensors | 5
26 | Feb | Window Glazing | High Winds | 0.8 | Medium | 14 | Glass Breakage | Specialized storage | 4
27 | Mar | External Render | Sandstorm | 0.75 | Large | 21 | Material Shortage | Local supplier backup | 5
28 | Mar | Site Surveying | Dust | 0.9 | Infrastructure | 15 | Equipment Error | Laser calibration | 2
29 | Apr | Solar Panel Install | Clear | 1 | Mega | 30 | Customs Delay | Early clearing | 10
30 | Apr | Data Cabling | Clear | 0.9 | Large | 25 | Cable Shortage | Bulk ordering | 4
31 | May | Asphalt Paving | High Heat | 0.85 | Infrastructure | 14 | Batch Plant Delay | Priority scheduling | 5
32 | May | Pool Filtration | Clear | 1 | Small | 12 | Normal | System pre-test | 0
33 | Jun | Slab Pouring | Extreme Heat | 0.8 | Giga | 30 | Concrete Supply | Chilled water usage | 4
34 | Jun | Steel Erection | Extreme Heat | 0.75 | Mega | 40 | Normal | Night shift work | 6
35 | Jul | HVAC Testing | Extreme Heat | 0.85 | Large | 20 | Unit Failure | Spare parts on-site | 8
36 | Jul | Exterior Tiling | Extreme Heat | 0.7 | Medium | 15 | Adhesive Delay | Heat-resistant glue | 5
37 | Aug | Indoor Paint | Clear | 1 | Small | 10 | Normal | Air conditioning | 0
38 | Aug | Lift Installation | Extreme Heat | 0.85 | Large | 45 | Parts Missing | Inventory tracking | 9
39 | Sep | Fire Sprinklers | Clear | 0.95 | Mega | 35 | Normal | Pressure testing | 2
40 | Sep | Marble Flooring | Clear | 0.8 | Medium | 20 | Logistic Delay | Direct factory shipping | 6
41 | Oct | Grid Connection | Clear | 1 | Infrastructure | 60 | SEC Approval | Gov Liaison support | 15
42 | Oct | Substation Setup | Clear | 1 | Giga | 90 | Transformer Delay | Temporary power | 20
43 | Nov | Piling Works | Heavy Rain | 1 | Mega | 40 | Muddy Site | Gravel access roads | 12
44 | Nov | Basement Isolation | Rain | 0.9 | Large | 14 | Pump Failure | Backup dewatering | 6
45 | Dec | Landscaping | Clear | 1 | Medium | 30 | Plant Mortality | Winter protection | 4
46 | Dec | Key Handover | Clear | 1 | Small | 5 | Admin Issues | Early document prep | 2
47 | Oct | Water Insulation | Light Rain | 1 | Large | 12 | Normal | Surface drying machines | 4
48 | Oct | Grid Connection | Clear | 1 | Infrastructure | 90 | Meter Delay | Early SEC coordination | 15
49 | Oct | Concrete Works | Clear | 1 | Giga | 25 | Material Batch | Quality control on-site | 3
50 | Oct | Security Systems | Clear | 1 | Mega | 30 | Sensor Shortage | Pre-order specialized tech | 8
51 | Nov | Excavation | Rain | 0.9 | Infrastructure | 20 | Normal | Drainage & slope prep | 5
52 | Nov | Foundations | Heavy Rain | 1 | Mega | 40 | Normal | Dewatering system | 4
53 | Nov | Gas Systems | Clear | 0.85 | Large | 25 | Valve Delay | Safety valve backup | 7
54 | Nov | Footing Pouring | Rain | 0.9 | Medium | 15 | Normal | Temporary covers | 4
55 | Nov | Site Drilling | Heavy Rain | 1 | Infrastructure | 60 | Hard Rocks | Specialized drill bits | 12
56 | Dec | Decoration | Clear | 1 | Small | 14 | Normal | Skilled artisan team | 0
57 | Dec | Glass Fitting | Clear/Cold | 1 | Large | 20 | Broken Cargo | 10% extra buffer stock | 12
58 | Dec | Final Handover | Clear | 1 | Mega | 45 | Admin Issues | Gov liaison officer | 10
59 | Dec | Smart Systems | Clear | 1 | Giga | 60 | Sensor Delay | Direct air-freight | 10
60 | Dec | Wooden Works | Clear | 0.85 | Medium | 15 | Humidity Issue | Climate-controlled storage | 3
61 | Jan | Piling Works | Rain | 0.9 | Giga | 90 | Normal | Soil consolidation | 8
62 | Jan | Basement Slab | Clear/Cold | 1 | Large | 20 | Additive Delay | Thermal blankets | 4
63 | Feb | Curtain Wall | High Winds | 0.75 | Mega | 45 | Supply Delay | Shift-based installation | 9
64 | Feb | Fire Alarm | Clear | 1 | Medium | 15 | Normal | Pre-testing circuits | 0
65 | Mar | Plastering | Sandstorm | 0.8 | Large | 20 | Normal | Enclosed working area | 5
66 | Mar | Outdoor Paving | Dust | 0.9 | Infrastructure | 30 | Asphalt Shortage | Priority batching | 4
67 | Apr | Solar Farm | Clear | 1 | Giga | 120 | Port Delay | Local storage buffer | 18
68 | Apr | Data Center | Clear | 0.95 | Mega | 60 | Cooling Units | Factory FAT testing | 10
69 | May | External Paint | Clear | 1 | Medium | 10 | Normal | UV resistant paint | 0
70 | May | Roof Insulation | High Heat | 0.9 | Small | 7 | Normal | Early morning shifts | 2
71 | Jun | Bridge Piers | Extreme Heat | 0.8 | Infrastructure | 60 | Steel Supply | Cooling during curing | 12
72 | Jun | Concrete Slab | Extreme Heat | 0.85 | Giga | 30 | Normal | Chilled water usage | 5
73 | Jul | HVAC Chillers | Extreme Heat | 0.85 | Mega | 40 | Unit Delay | Temporary ventilation | 14
74 | Jul | Swimming Pool | Extreme Heat | 0.7 | Small | 20 | Normal | Night shift tiling | 6
75 | Aug | Irrigation | Extreme Heat | 0.9 | Large | 25 | Pump Delay | Water truck support | 7
76 | Aug | MEP Commissioning | Extreme Heat | 0.8 | Giga | 50 | Technical Error | Expert team on-site | 10
77 | Sep | Interior Marble | Clear | 0.75 | Large | 30 | Cutting Error | Digital measurement | 8
78 | Sep | Kitchen Fixtures | Dust | 0.9 | Medium | 15 | Supply Delay | Local carpentry backup | 5
79 | Oct | Substation | Clear | 1 | Giga | 90 | Transformer Issue | Redundant units | 25
80 | Oct | Landscape Trees | Clear | 1 | Mega | 30 | Plant Disease | Expert horticulturalist | 6
81 | Nov | Sewerage Pipes | Rain | 0.85 | Infrastructure | 45 | Normal | Trench shoring | 8
82 | Nov | Elevator Install | Rain | 0.9 | Large | 40 | Parts Missing | Digital inventory tracking | 12
83 | Dec | Security Gates | Clear | 1 | Infrastructure | 25 | Software Bug | Remote support team | 5
84 | Dec | Sound Systems | Clear | 1 | Medium | 10 | Normal | Calibration experts | 0
85 | Jan | Site Clearing | Rain | 0.8 | Small | 5 | Normal | Heavy machinery | 3
86 | Feb | Signaling Sys | High Winds | 0.85 | Infrastructure | 60 | Tech Delay | Government approval | 15
87 | Mar | Gypsum Works | Sandstorm | 0.9 | Medium | 15 | Normal | Indoor dust protection | 2
88 | Apr | Street Lighting | Clear | 1 | Infrastructure | 40 | Pole Delay | Direct sourcing | 6
89 | May | Building Management | Clear | 1 | Mega | 30 | System Integration | BIM link-up | 7
90 | Jun | Pre-cast Walls | Extreme Heat | 0.9 | Giga | 45 | Normal | Factory-controlled env | 3
91 | Jul | Underground Tank | Extreme Heat | 0.75 | Large | 25 | Normal | Waterproofing additives | 6
92 | Aug | False Ceilings | High Heat | 0.95 | Medium | 12 | Material Shortage | Alternative suppliers | 4
93 | Sep | Fire Suppression | Clear | 1 | Mega | 20 | Valve Delay | Pre-installation audit | 5
94 | Oct | Fiber Optics | Clear | 1 | Infrastructure | 35 | Normal | Directional drilling | 2
95 | Nov | Retaining Walls | Heavy Rain | 0.85 | Giga | 50 | Logistic Delay | Temporary site access | 14
96 | Dec | Handrail Install | Clear | 1 | Small | 7 | Normal | Local workshop | 0
97 | Jan | Site Compaction | Rain | 0.8 | Large | 10 | Normal | Moisture control | 5
98 | Feb | Power Testing | High Winds | 0.9 | Mega | 15 | Safety Issue | High-voltage permits | 8
99 | Mar | Final Painting | Dust | 0.85 | Medium | 10 | Normal | Air-scrubbing units | 3
100 | Dec | Project Handover | Clear | 1 | Giga | 30 | Admin Issues | Final Ministerial Sign-off | 20