## Sheet1
No. | Date | Activity | Weather | Labor | Project Size | Planned Days | Supply Chain | Risk Mitigation | Delay
1 | 2025-01-03 | Foundations | Cool / Windy | 0.95 | Large | 14 | Normal | Soil stabilization | 4
2 | 2025-01-04 | Concrete Pouring | Cool / Clear | 1 | Mega | 20 | Pump Failure | Backup pump on-site | 2
3 | 2025-01-05 | Steel Structure | Cool / Windy | 0.8 | Infrastructure | 45 | Steel Shortage | Early procurement | 9
4 | 2025-01-06 | Electrical (Main) | Cool / Clear | 0.9 | Giga | 60 | Transformer Delay | Temporary generators | 15
5 | 2025-01-07 | Exterior Facades | Cool / Chance of Rain | 0.7 | Large | 30 | Glass Breakage | Specialized storage | 6
6 | 2025-01-08 | HVAC Ducting | Cool / Windy | 0.85 | Mega | 25 | Design Clash (BIM) | BIM Coordination | 5
7 | 2025-01-09 | Interior Plaster | Cool / Chance of Rain | 1 | Medium | 15 | Normal | Accelerated drying | 0
8 | 2025-01-10 | Elevator Shafts | Cool / Clear | 1 | Large | 40 | Customs Delay | Early shipping | 12
9 | 2025-01-11 | Roof Waterproofing | Cool / Clear | 0.9 | Medium | 10 | Normal | Night shift work | 3
10 | 2025-01-12 | Infrastructure Pipes | Cool / Clear | 0.95 | Infrastructure | 90 | Underground Utility | Utility mapping | 10
11 | 2025-01-13 | Slab Casting | Cool / Windy | 0.8 | Giga | 20 | Normal | Chilled water mix | 4
12 | 2025-01-14 | External Cladding | Cool / Windy | 0.75 | Large | 25 | Supply Shortage | Local sourcing | 7
13 | 2025-01-15 | Landscape/Trees | Cool / Windy | 0.85 | Mega | 30 | Plant Mortality | Automated irrigation | 8
14 | 2025-01-16 | Road Paving | Cool / Windy | 0.7 | Infrastructure | 15 | Asphalt Delay | Batch plant priority | 5
15 | 2025-01-17 | Final Finishing | Cool / Cloudy | 0.9 | Small | 20 | Normal | Air-conditioned site | 0
16 | 2025-01-18 | Fire Fighting Sys | Cool / Windy | 1 | Large | 25 | Valve Shortage | Pre-ordering valves | 4
17 | 2025-01-19 | Smart Home Hub | Cool / Chance of Rain | 0.95 | Medium | 10 | Firmware Issue | Remote tech support | 3
18 | 2025-01-20 | Swimming Pools | Cool / Chance of Rain | 0.9 | Large | 30 | Normal | Water testing | 2
19 | 2025-01-21 | Main Substation | Cool / Cloudy | 1 | Giga | 120 | SEC Approval | Gov Liaison Officer | 20
20 | 2025-01-22 | Excavation | Cool / Clear | 1 | Large | 15 | Muddy Terrain | Gravel access roads | 7
21 | 2025-01-23 | Smart Systems | Cool / Cloudy | 1 | Mega | 15 | Tech Setup Issue | Early software testing | 7
22 | 2025-01-24 | Final Inspection | Cool / Windy | 1 | Medium | 10 | Compliance Issue | Pre-audit check | 12
23 | 2025-01-25 | Soil Compaction | Cool / Clear | 0.85 | Infrastructure | 20 | Normal | Soil stabilization | 6
24 | 2025-01-26 | Concrete Curing | Cool / Chance of Rain | 0.95 | Large | 7 | Additive Delay | Accelerated curing agents | 3
25 | 2025-01-27 | Tower Crane Ops | Cool / Chance of Rain | 0.7 | Giga | 120 | Safety Protocol | Wind speed sensors | 5
26 | 2025-01-28 | Window Glazing | Cool / Clear | 0.8 | Medium | 14 | Glass Breakage | Specialized storage | 4
27 | 2025-01-29 | External Render | Cool / Windy | 0.75 | Large | 21 | Material Shortage | Local supplier backup | 5
28 | 2025-01-30 | Site Surveying | Cool / Windy | 0.9 | Infrastructure | 15 | Equipment Error | Laser calibration | 2
29 | 2025-01-31 | Solar Panel Install | Cool / Cloudy | 1 | Mega | 30 | Customs Delay | Early clearing | 10
30 | 2025-02-01 | Data Cabling | Cool / Cloudy | 0.9 | Large | 25 | Cable Shortage | Bulk ordering | 4
31 | 2025-02-02 | Asphalt Paving | Cool / Cloudy | 0.85 | Infrastructure | 14 | Batch Plant Delay | Priority scheduling | 5
32 | 2025-02-03 | Pool Filtration | Cool / Windy | 1 | Small | 12 | Normal | System pre-test | 0
33 | 2025-02-04 | Slab Pouring | Cool / Clear | 0.8 | Giga | 30 | Concrete Supply | Chilled water usage | 4
34 | 2025-02-05 | Steel Erection | Cool / Chance of Rain | 0.75 | Mega | 40 | Normal | Night shift work | 6
35 | 2025-02-06 | HVAC Testing | Cool / Chance of Rain | 0.85 | Large | 20 | Unit Failure | Spare parts on-site | 8
36 | 2025-02-07 | Exterior Tiling | Cool / Cloudy | 0.7 | Medium | 15 | Adhesive Delay | Heat-resistant glue | 5
37 | 2025-02-08 | Indoor Paint | Cool / Clear | 1 | Small | 10 | Normal | Air conditioning | 0
38 | 2025-02-09 | Lift Installation | Cool / Cloudy | 0.85 | Large | 45 | Parts Missing | Inventory tracking | 9
39 | 2025-02-10 | Fire Sprinklers | Cool / Clear | 0.95 | Mega | 35 | Normal | Pressure testing | 2
40 | 2025-02-11 | Marble Flooring | Cool / Windy | 0.8 | Medium | 20 | Logistic Delay | Direct factory shipping | 6
41 | 2025-02-12 | Grid Connection | Cool / Windy | 1 | Infrastructure | 60 | SEC Approval | Gov Liaison support | 15
42 | 2025-02-13 | Substation Setup | Cool / Clear | 1 | Giga | 90 | Transformer Delay | Temporary power | 20
43 | 2025-02-14 | Piling Works | Cool / Chance of Rain | 1 | Mega | 40 | Muddy Site | Gravel access roads | 12
44 | 2025-02-15 | Basement Isolation | Cool / Chance of Rain | 0.9 | Large | 14 | Pump Failure | Backup dewatering | 6
45 | 2025-02-16 | Landscaping | Cool / Cloudy | 1 | Medium | 30 | Plant Mortality | Winter protection | 4
46 | 2025-02-17 | Key Handover | Cool / Chance of Rain | 1 | Small | 5 | Admin Issues | Early document prep | 2
47 | 2025-02-18 | Water Insulation | Cool / Chance of Rain | 1 | Large | 12 | Normal | Surface drying machines | 4
48 | 2025-02-19 | Grid Connection | Cool / Chance of Rain | 1 | Infrastructure | 90 | Meter Delay | Early SEC coordination | 15
49 | 2025-02-20 | Concrete Works | Cool / Windy | 1 | Giga | 25 | Material Batch | Quality control on-site | 3
50 | 2025-02-21 | Security Systems | Cool / Clear | 1 | Mega | 30 | Sensor Shortage | Pre-order specialized tech | 8
51 | 2025-02-22 | Excavation | Cool / Clear | 0.9 | Infrastructure | 20 | Normal | Drainage & slope prep | 5
52 | 2025-02-23 | Foundations | Cool / Clear | 1 | Mega | 40 | Normal | Dewatering system | 4
53 | 2025-02-24 | Gas Systems | Cool / Chance of Rain | 0.85 | Large | 25 | Valve Delay | Safety valve backup | 7
54 | 2025-02-25 | Footing Pouring | Cool / Cloudy | 0.9 | Medium | 15 | Normal | Temporary covers | 4
55 | 2025-02-26 | Site Drilling | Cool / Chance of Rain | 1 | Infrastructure | 60 | Hard Rocks | Specialized drill bits | 12
56 | 2025-02-27 | Decoration | Cool / Windy | 1 | Small | 14 | Normal | Skilled artisan team | 0
57 | 2025-02-28 | Glass Fitting | Cool / Cloudy | 1 | Large | 20 | Broken Cargo | 10% extra buffer stock | 12
58 | 2025-03-01 | Final Handover | Mild / Dusty | 1 | Mega | 45 | Admin Issues | Gov liaison officer | 10
59 | 2025-03-02 | Smart Systems | Mild / Windy | 1 | Giga | 60 | Sensor Delay | Direct air-freight | 10
60 | 2025-03-03 | Wooden Works | Mild / Clear | 0.85 | Medium | 15 | Humidity Issue | Climate-controlled storage | 3
61 | 2025-03-04 | Piling Works | Mild / Clear | 0.9 | Giga | 90 | Normal | Soil consolidation | 8
62 | 2025-03-05 | Basement Slab | Mild / Windy | 1 | Large | 20 | Additive Delay | Thermal blankets | 4
63 | 2025-03-06 | Curtain Wall | Mild / Windy | 0.75 | Mega | 45 | Supply Delay | Shift-based installation | 9
64 | 2025-03-07 | Fire Alarm | Mild / Clear | 1 | Medium | 15 | Normal | Pre-testing circuits | 0
65 | 2025-03-08 | Plastering | Mild / Dusty | 0.8 | Large | 20 | Normal | Enclosed working area | 5
66 | 2025-03-09 | Outdoor Paving | Mild / Dusty | 0.9 | Infrastructure | 30 | Asphalt Shortage | Priority batching | 4
67 | 2025-03-10 | Solar Farm | Mild / Dusty | 1 | Giga | 120 | Port Delay | Local storage buffer | 18
68 | 2025-03-11 | Data Center | Mild / Windy | 0.95 | Mega | 60 | Cooling Units | Factory FAT testing | 10
69 | 2025-03-12 | External Paint | Mild / Clear | 1 | Medium | 10 | Normal | UV resistant paint | 0
70 | 2025-03-13 | Roof Insulation | Mild / Clear | 0.9 | Small | 7 | Normal | Early morning shifts | 2
71 | 2025-03-14 | Bridge Piers | Mild / Dusty | 0.8 | Infrastructure | 60 | Steel Supply | Cooling during curing | 12
72 | 2025-03-15 | Concrete Slab | Mild / Dusty | 0.85 | Giga | 30 | Normal | Chilled water usage | 5
73 | 2025-03-16 | HVAC Chillers | Mild / Dusty | 0.85 | Mega | 40 | Unit Delay | Temporary ventilation | 14
74 | 2025-03-17 | Swimming Pool | Mild / Dusty | 0.7 | Small | 20 | Normal | Night shift tiling | 6
75 | 2025-03-18 | Irrigation | Mild / Windy | 0.9 | Large | 25 | Pump Delay | Water truck support | 7
76 | 2025-03-19 | MEP Commissioning | Mild / Windy | 0.8 | Giga | 50 | Technical Error | Expert team on-site | 10
77 | 2025-03-20 | Interior Marble | Mild / Clear | 0.75 | Large | 30 | Cutting Error | Digital measurement | 8
78 | 2025-03-21 | Kitchen Fixtures | Mild / Windy | 0.9 | Medium | 15 | Supply Delay | Local carpentry backup | 5
79 | 2025-03-22 | Substation | Mild / Clear | 1 | Giga | 90 | Transformer Issue | Redundant units | 25
80 | 2025-03-23 | Landscape Trees | Mild / Clear | 1 | Mega | 30 | Plant Disease | Expert horticulturalist | 6
81 | 2025-03-24 | Sewerage Pipes | Mild / Dusty | 0.85 | Infrastructure | 45 | Normal | Trench shoring | 8
82 | 2025-03-25 | Elevator Install | Mild / Clear | 0.9 | Large | 40 | Parts Missing | Digital inventory tracking | 12
83 | 2025-03-26 | Security Gates | Mild / Windy | 1 | Infrastructure | 25 | Software Bug | Remote support team | 5
84 | 2025-03-27 | Sound Systems | Mild / Windy | 1 | Medium | 10 | Normal | Calibration experts | 0
85 | 2025-03-28 | Site Clearing | Mild / Clear | 0.8 | Small | 5 | Normal | Heavy machinery | 3
86 | 2025-03-29 | Signaling Sys | Mild / Windy | 0.85 | Infrastructure | 60 | Tech Delay | Government approval | 15
87 | 2025-03-30 | Gypsum Works | Mild / Windy | 0.9 | Medium | 15 | Normal | Indoor dust protection | 2
88 | 2025-03-31 | Street Lighting | Mild / Clear | 1 | Infrastructure | 40 | Pole Delay | Direct sourcing | 6
89 | 2025-04-01 | Building Management | Mild / Dusty | 1 | Mega | 30 | System Integration | BIM link-up | 7
90 | 2025-04-02 | Pre-cast Walls | Mild / Windy | 0.9 | Giga | 45 | Normal | Factory-controlled env | 3
91 | 2025-04-03 | Underground Tank | Mild / Windy | 0.75 | Large | 25 | Normal | Waterproofing additives | 6
92 | 2025-04-04 | False Ceilings | Mild / Clear | 0.95 | Medium | 12 | Material Shortage | Alternative suppliers | 4
93 | 2025-04-05 | Fire Suppression | Mild / Clear | 1 | Mega | 20 | Valve Delay | Pre-installation audit | 5
94 | 2025-04-06 | Fiber Optics | Mild / Dusty | 1 | Infrastructure | 35 | Normal | Directional drilling | 2
95 | 2025-04-07 | Retaining Walls | Mild / Dusty | 0.85 | Giga | 50 | Logistic Delay | Temporary site access | 14
96 | 2025-04-08 | Handrail Install | Mild / Windy | 1 | Small | 7 | Normal | Local workshop | 0
97 | 2025-04-09 | Site Compaction | Mild / Clear | 0.8 | Large | 10 | Normal | Moisture control | 5
98 | 2025-04-10 | Power Testing | Mild / Windy | 0.9 | Mega | 15 | Safety Issue | High-voltage permits | 8
99 | 2025-04-11 | Final Painting | Mild / Windy | 0.85 | Medium | 10 | Normal | Air-scrubbing units | 3
100 | 2025-04-12 | Project Handover | Mild / Windy | 1 | Giga | 30 | Admin Issues | Final Ministerial Sign-off | 20
101 | 2025-04-13 | Security Gates | Mild / Clear | 1 | Infrastructure | 25 | Software Bug | Remote support team | 4
102 | 2025-04-14 | Concrete Curing | Mild / Windy | 0.95 | Large | 7 | Additive Delay | Accelerated curing agents | 4
103 | 2025-04-15 | Irrigation | Mild / Dusty | 0.9 | Large | 25 | Pump Delay | Water truck support | 5
104 | 2025-04-16 | Exterior Tiling | Mild / Dusty | 0.7 | Medium | 15 | Adhesive Delay | Heat-resistant glue | 6
105 | 2025-04-17 | Fire Alarm | Mild / Clear | 1 | Medium | 15 | Normal | Pre-testing circuits | 0
106 | 2025-04-18 | Site Surveying | Mild / Windy | 0.9 | Infrastructure | 15 | Equipment Error | Laser calibration | 2
107 | 2025-04-19 | Bridge Piers | Mild / Clear | 0.8 | Infrastructure | 60 | Steel Supply | Cooling during curing | 10
108 | 2025-04-20 | Water Insulation | Mild / Clear | 1 | Large | 12 | Normal | Surface drying machines | 2
109 | 2025-04-21 | Gas Systems | Mild / Clear | 0.85 | Large | 25 | Valve Delay | Safety valve backup | 8
110 | 2025-04-22 | Landscape/Trees | Mild / Windy | 0.85 | Mega | 30 | Plant Mortality | Automated irrigation | 6
111 | 2025-04-23 | Slab Pouring | Mild / Dusty | 0.8 | Giga | 30 | Concrete Supply | Chilled water usage | 4
112 | 2025-04-24 | Swimming Pools | Mild / Windy | 0.9 | Large | 30 | Normal | Water testing | 2
113 | 2025-04-25 | Smart Home Hub | Mild / Windy | 0.95 | Medium | 10 | Firmware Issue | Remote tech support | 1
114 | 2025-04-26 | Road Paving | Mild / Dusty | 0.7 | Infrastructure | 15 | Asphalt Delay | Batch plant priority | 4
115 | 2025-04-27 | Wooden Works | Mild / Clear | 0.85 | Medium | 15 | Humidity Issue | Climate-controlled storage | 1
116 | 2025-04-28 | Substation Setup | Mild / Windy | 1 | Giga | 90 | Transformer Delay | Temporary power | 18
117 | 2025-04-29 | Building Management | Mild / Clear | 1 | Mega | 30 | System Integration | BIM link-up | 10
118 | 2025-04-30 | Steel Erection | Mild / Dusty | 0.75 | Mega | 40 | Normal | Night shift work | 8
119 | 2025-05-01 | Road Paving | Very Hot / Humid | 0.7 | Infrastructure | 15 | Asphalt Delay | Batch plant priority | 4
120 | 2025-05-02 | Slab Pouring | Very Hot / Humid | 0.8 | Giga | 30 | Concrete Supply | Chilled water usage | 3
121 | 2025-05-03 | Fire Alarm | Very Hot / Dry | 1 | Medium | 15 | Normal | Pre-testing circuits | 0
122 | 2025-05-04 | Fire Suppression | Very Hot / Dry | 1 | Mega | 20 | Valve Delay | Pre-installation audit | 8
123 | 2025-05-05 | Marble Flooring | Hot / Dry | 0.8 | Medium | 20 | Logistic Delay | Direct factory shipping | 5
124 | 2025-05-06 | Smart Systems | Hot / Dry | 1 | Mega | 15 | Tech Setup Issue | Early software testing | 7
125 | 2025-05-07 | Substation | Very Hot / Dry | 1 | Giga | 90 | Transformer Issue | Redundant units | 23
126 | 2025-05-08 | Bridge Piers | Hot / Dry | 0.8 | Infrastructure | 60 | Steel Supply | Cooling during curing | 13
127 | 2025-05-09 | Excavation | Very Hot / Dry | 0.9 | Infrastructure | 20 | Normal | Drainage & slope prep | 8
128 | 2025-05-10 | Street Lighting | Very Hot / Dry | 1 | Infrastructure | 40 | Pole Delay | Direct sourcing | 8
129 | 2025-05-11 | Outdoor Paving | Very Hot / Dry | 0.9 | Infrastructure | 30 | Asphalt Shortage | Priority batching | 6
130 | 2025-05-12 | Swimming Pool | Hot / Dry | 0.7 | Small | 20 | Normal | Night shift tiling | 7
131 | 2025-05-13 | Signaling Sys | Very Hot / Dry | 0.85 | Infrastructure | 60 | Tech Delay | Government approval | 18
132 | 2025-05-14 | Grid Connection | Very Hot / Humid | 1 | Infrastructure | 60 | SEC Approval | Gov Liaison support | 17
133 | 2025-05-15 | Swimming Pools | Very Hot / Dry | 0.9 | Large | 30 | Normal | Water testing | 5
134 | 2025-05-16 | Infrastructure Pipes | Very Hot / Dry | 0.95 | Infrastructure | 90 | Underground Utility | Utility mapping | 9
135 | 2025-05-17 | Building Management | Very Hot / Humid | 1 | Mega | 30 | System Integration | BIM link-up | 10
136 | 2025-05-18 | Grid Connection | Very Hot / Dry | 1 | Infrastructure | 60 | SEC Approval | Gov Liaison support | 16
137 | 2025-05-19 | Concrete Curing | Very Hot / Humid | 0.95 | Large | 7 | Additive Delay | Accelerated curing agents | 1
138 | 2025-05-20 | Landscaping | Very Hot / Dry | 1 | Medium | 30 | Plant Mortality | Winter protection | 6
139 | 2025-05-21 | Concrete Slab | Very Hot / Humid | 0.85 | Giga | 30 | Normal | Chilled water usage | 6
140 | 2025-05-22 | Landscape Trees | Hot / Dry | 1 | Mega | 30 | Plant Disease | Expert horticulturalist | 8
141 | 2025-05-23 | Pool Filtration | Very Hot / Humid | 1 | Small | 12 | Normal | System pre-test | 3
142 | 2025-05-24 | Footing Pouring | Very Hot / Humid | 0.9 | Medium | 15 | Normal | Temporary covers | 4
143 | 2025-05-25 | Lift Installation | Very Hot / Dry | 0.85 | Large | 45 | Parts Missing | Inventory tracking | 10
144 | 2025-05-26 | Landscape Trees | Hot / Dry | 1 | Mega | 30 | Plant Disease | Expert horticulturalist | 7
145 | 2025-05-27 | Infrastructure Pipes | Hot / Dry | 0.95 | Infrastructure | 90 | Underground Utility | Utility mapping | 8
146 | 2025-05-28 | Main Substation | Very Hot / Humid | 1 | Giga | 120 | SEC Approval | Gov Liaison Officer | 18
147 | 2025-05-29 | Key Handover | Very Hot / Dry | 1 | Small | 5 | Admin Issues | Early document prep | 1
148 | 2025-05-30 | Solar Farm | Very Hot / Humid | 1 | Giga | 120 | Port Delay | Local storage buffer | 17
149 | 2025-05-31 | Footing Pouring | Very Hot / Humid | 0.9 | Medium | 15 | Normal | Temporary covers | 2
150 | 2025-06-01 | Window Glazing | Very Hot / Humid | 0.8 | Medium | 14 | Glass Breakage | Specialized storage | 5
151 | 2025-06-02 | Fire Suppression | Very Hot / Humid | 1 | Mega | 20 | Valve Delay | Pre-installation audit | 6
152 | 2025-06-03 | Concrete Curing | Hot / Dry | 0.95 | Large | 7 | Additive Delay | Accelerated curing agents | 6
153 | 2025-06-04 | Excavation | Very Hot / Humid | 0.9 | Infrastructure | 20 | Normal | Drainage & slope prep | 6
154 | 2025-06-05 | Exterior Facades | Very Hot / Humid | 0.7 | Large | 30 | Glass Breakage | Specialized storage | 4
155 | 2025-06-06 | Bridge Piers | Very Hot / Dry | 0.8 | Infrastructure | 60 | Steel Supply | Cooling during curing | 15
156 | 2025-06-07 | Key Handover | Hot / Dry | 1 | Small | 5 | Admin Issues | Early document prep | 4
157 | 2025-06-08 | Kitchen Fixtures | Very Hot / Dry | 0.9 | Medium | 15 | Supply Delay | Local carpentry backup | 7
158 | 2025-06-09 | Concrete Pouring | Hot / Dry | 1 | Mega | 20 | Pump Failure | Backup pump on-site | 4
159 | 2025-06-10 | Infrastructure Pipes | Very Hot / Dry | 0.95 | Infrastructure | 90 | Underground Utility | Utility mapping | 12
160 | 2025-06-11 | Kitchen Fixtures | Hot / Dry | 0.9 | Medium | 15 | Supply Delay | Local carpentry backup | 4
161 | 2025-06-12 | Concrete Slab | Hot / Dry | 0.85 | Giga | 30 | Normal | Chilled water usage | 5
162 | 2025-06-13 | Building Management | Very Hot / Humid | 1 | Mega | 30 | System Integration | BIM link-up | 9
163 | 2025-06-14 | Concrete Curing | Very Hot / Dry | 0.95 | Large | 7 | Additive Delay | Accelerated curing agents | 6
164 | 2025-06-15 | Exterior Tiling | Very Hot / Humid | 0.7 | Medium | 15 | Adhesive Delay | Heat-resistant glue | 8
165 | 2025-06-16 | Piling Works | Hot / Dry | 1 | Mega | 40 | Muddy Site | Gravel access roads | 14
166 | 2025-06-17 | Street Lighting | Very Hot / Humid | 1 | Infrastructure | 40 | Pole Delay | Direct sourcing | 8
167 | 2025-06-18 | Main Substation | Hot / Dry | 1 | Giga | 120 | SEC Approval | Gov Liaison Officer | 23
168 | 2025-06-19 | External Cladding | Hot / Dry | 0.75 | Large | 25 | Supply Shortage | Local sourcing | 10
169 | 2025-06-20 | Water Insulation | Very Hot / Humid | 1 | Large | 12 | Normal | Surface drying machines | 6
170 | 2025-06-21 | Final Painting | Very Hot / Humid | 0.85 | Medium | 10 | Normal | Air-scrubbing units | 2
171 | 2025-06-22 | Exterior Tiling | Very Hot / Humid | 0.7 | Medium | 15 | Adhesive Delay | Heat-resistant glue | 8
172 | 2025-06-23 | HVAC Ducting | Very Hot / Dry | 0.85 | Mega | 25 | Design Clash (BIM) | BIM Coordination | 7
173 | 2025-06-24 | Marble Flooring | Very Hot / Humid | 0.8 | Medium | 20 | Logistic Delay | Direct factory shipping | 8
174 | 2025-06-25 | Key Handover | Hot / Dry | 1 | Small | 5 | Admin Issues | Early document prep | 2
175 | 2025-06-26 | Sewerage Pipes | Very Hot / Humid | 0.85 | Infrastructure | 45 | Normal | Trench shoring | 8
176 | 2025-06-27 | Final Handover | Very Hot / Humid | 1 | Mega | 45 | Admin Issues | Gov liaison officer | 8
177 | 2025-06-28 | Curtain Wall | Very Hot / Humid | 0.75 | Mega | 45 | Supply Delay | Shift-based installation | 12
178 | 2025-06-29 | Final Inspection | Very Hot / Dry | 1 | Medium | 10 | Compliance Issue | Pre-audit check | 14
179 | 2025-06-30 | Marble Flooring | Hot / Dry | 0.8 | Medium | 20 | Logistic Delay | Direct factory shipping | 5
180 | 2025-07-01 | Asphalt Paving | Very Hot / Dry | 0.85 | Infrastructure | 14 | Batch Plant Delay | Priority scheduling | 7
181 | 2025-07-02 | Slab Casting | Hot / Dry | 0.8 | Giga | 20 | Normal | Chilled water mix | 7
182 | 2025-07-03 | Piling Works | Hot / Dry | 0.9 | Giga | 90 | Normal | Soil consolidation | 8
183 | 2025-07-04 | External Render | Hot / Dry | 0.75 | Large | 21 | Material Shortage | Local supplier backup | 5
184 | 2025-07-05 | Steel Erection | Very Hot / Humid | 0.75 | Mega | 40 | Normal | Night shift work | 7
185 | 2025-07-06 | Interior Marble | Very Hot / Dry | 0.75 | Large | 30 | Cutting Error | Digital measurement | 11
186 | 2025-07-07 | HVAC Ducting | Very Hot / Dry | 0.85 | Mega | 25 | Design Clash (BIM) | BIM Coordination | 7
187 | 2025-07-08 | Key Handover | Very Hot / Dry | 1 | Small | 5 | Admin Issues | Early document prep | 1
188 | 2025-07-09 | Fire Sprinklers | Hot / Dry | 0.95 | Mega | 35 | Normal | Pressure testing | 1
189 | 2025-07-10 | Gypsum Works | Hot / Dry | 0.9 | Medium | 15 | Normal | Indoor dust protection | 2
190 | 2025-07-11 | Window Glazing | Hot / Dry | 0.8 | Medium | 14 | Glass Breakage | Specialized storage | 2
191 | 2025-07-12 | Swimming Pools | Very Hot / Dry | 0.9 | Large | 30 | Normal | Water testing | 5
192 | 2025-07-13 | Smart Home Hub | Very Hot / Dry | 0.95 | Medium | 10 | Firmware Issue | Remote tech support | 4
193 | 2025-07-14 | Fiber Optics | Hot / Dry | 1 | Infrastructure | 35 | Normal | Directional drilling | 5
194 | 2025-07-15 | Grid Connection | Very Hot / Humid | 1 | Infrastructure | 60 | SEC Approval | Gov Liaison support | 18
195 | 2025-07-16 | Final Finishing | Hot / Dry | 0.9 | Small | 20 | Normal | Air-conditioned site | 0
196 | 2025-07-17 | Elevator Install | Hot / Dry | 0.9 | Large | 40 | Parts Missing | Digital inventory tracking | 14
197 | 2025-07-18 | Swimming Pools | Very Hot / Humid | 0.9 | Large | 30 | Normal | Water testing | 5
198 | 2025-07-19 | Fire Fighting Sys | Hot / Dry | 1 | Large | 25 | Valve Shortage | Pre-ordering valves | 2
199 | 2025-07-20 | Marble Flooring | Very Hot / Humid | 0.8 | Medium | 20 | Logistic Delay | Direct factory shipping | 9
200 | 2025-07-21 | Signaling Sys | Very Hot / Humid | 0.85 | Infrastructure | 60 | Tech Delay | Government approval | 14
201 | 2025-07-22 | Smart Systems | Hot / Dry | 1 | Giga | 60 | Sensor Delay | Direct air-freight | 12
202 | 2025-07-23 | Elevator Install | Very Hot / Dry | 0.9 | Large | 40 | Parts Missing | Digital inventory tracking | 10
203 | 2025-07-24 | Steel Structure | Very Hot / Dry | 0.8 | Infrastructure | 45 | Steel Shortage | Early procurement | 8
204 | 2025-07-25 | Building Management | Very Hot / Dry | 1 | Mega | 30 | System Integration | BIM link-up | 9
205 | 2025-07-26 | Indoor Paint | Very Hot / Dry | 1 | Small | 10 | Normal | Air conditioning | 0
206 | 2025-07-27 | Retaining Walls | Very Hot / Dry | 0.85 | Giga | 50 | Logistic Delay | Temporary site access | 14
207 | 2025-07-28 | Final Painting | Hot / Dry | 0.85 | Medium | 10 | Normal | Air-scrubbing units | 5
208 | 2025-07-29 | Kitchen Fixtures | Very Hot / Dry | 0.9 | Medium | 15 | Supply Delay | Local carpentry backup | 3
209 | 2025-07-30 | Infrastructure Pipes | Very Hot / Dry | 0.95 | Infrastructure | 90 | Underground Utility | Utility mapping | 9
210 | 2025-07-31 | Landscape Trees | Hot / Dry | 1 | Mega | 30 | Plant Disease | Expert horticulturalist | 9
211 | 2025-08-01 | Smart Systems | Hot / Dry | 1 | Giga | 60 | Sensor Delay | Direct air-freight | 13
212 | 2025-08-02 | Concrete Slab | Very Hot / Dry | 0.85 | Giga | 30 | Normal | Chilled water usage | 6
213 | 2025-08-03 | Substation | Very Hot / Humid | 1 | Giga | 90 | Transformer Issue | Redundant units | 26
214 | 2025-08-04 | Soil Compaction | Very Hot / Dry | 0.85 | Infrastructure | 20 | Normal | Soil stabilization | 8
215 | 2025-08-05 | Excavation | Very Hot / Dry | 1 | Large | 15 | Muddy Terrain | Gravel access roads | 5
216 | 2025-08-06 | HVAC Ducting | Very Hot / Dry | 0.85 | Mega | 25 | Design Clash (BIM) | BIM Coordination | 6
217 | 2025-08-07 | Electrical (Main) | Very Hot / Dry | 0.9 | Giga | 60 | Transformer Delay | Temporary generators | 15
218 | 2025-08-08 | Site Clearing | Very Hot / Humid | 0.8 | Small | 5 | Normal | Heavy machinery | 2
219 | 2025-08-09 | Solar Panel Install | Hot / Dry | 1 | Mega | 30 | Customs Delay | Early clearing | 9
220 | 2025-08-10 | Underground Tank | Hot / Dry | 0.75 | Large | 25 | Normal | Waterproofing additives | 9
221 | 2025-08-11 | Lift Installation | Hot / Dry | 0.85 | Large | 45 | Parts Missing | Inventory tracking | 12
222 | 2025-08-12 | Fire Suppression | Very Hot / Humid | 1 | Mega | 20 | Valve Delay | Pre-installation audit | 7
223 | 2025-08-13 | Building Management | Very Hot / Humid | 1 | Mega | 30 | System Integration | BIM link-up | 7
224 | 2025-08-14 | Building Management | Very Hot / Dry | 1 | Mega | 30 | System Integration | BIM link-up | 10
225 | 2025-08-15 | Asphalt Paving | Very Hot / Humid | 0.85 | Infrastructure | 14 | Batch Plant Delay | Priority scheduling | 7
226 | 2025-08-16 | Power Testing | Hot / Dry | 0.9 | Mega | 15 | Safety Issue | High-voltage permits | 7
227 | 2025-08-17 | Gas Systems | Hot / Dry | 0.85 | Large | 25 | Valve Delay | Safety valve backup | 6
228 | 2025-08-18 | Swimming Pools | Very Hot / Humid | 0.9 | Large | 30 | Normal | Water testing | 0
229 | 2025-08-19 | Pool Filtration | Very Hot / Dry | 1 | Small | 12 | Normal | System pre-test | 0
230 | 2025-08-20 | Grid Connection | Very Hot / Dry | 1 | Infrastructure | 90 | Meter Delay | Early SEC coordination | 13
231 | 2025-08-21 | Swimming Pools | Very Hot / Humid | 0.9 | Large | 30 | Normal | Water testing | 5
232 | 2025-08-22 | Asphalt Paving | Hot / Dry | 0.85 | Infrastructure | 14 | Batch Plant Delay | Priority scheduling | 7
233 | 2025-08-23 | Marble Flooring | Very Hot / Humid | 0.8 | Medium | 20 | Logistic Delay | Direct factory shipping | 4
234 | 2025-08-24 | Street Lighting | Very Hot / Humid | 1 | Infrastructure | 40 | Pole Delay | Direct sourcing | 7
235 | 2025-08-25 | Irrigation | Very Hot / Humid | 0.9 | Large | 25 | Pump Delay | Water truck support | 9
236 | 2025-08-26 | Substation Setup | Hot / Dry | 1 | Giga | 90 | Transformer Delay | Temporary power | 23
237 | 2025-08-27 | Pre-cast Walls | Very Hot / Humid | 0.9 | Giga | 45 | Normal | Factory-controlled env | 5
238 | 2025-08-28 | Final Handover | Very Hot / Dry | 1 | Mega | 45 | Admin Issues | Gov liaison officer | 10
239 | 2025-08-29 | Grid Connection | Hot / Dry | 1 | Infrastructure | 90 | Meter Delay | Early SEC coordination | 13
240 | 2025-08-30 | Elevator Shafts | Very Hot / Dry | 1 | Large | 40 | Customs Delay | Early shipping | 15
241 | 2025-08-31 | Concrete Works | Very Hot / Humid | 1 | Giga | 25 | Material Batch | Quality control on-site | 1
242 | 2025-09-01 | Power Testing | Very Hot / Humid | 0.9 | Mega | 15 | Safety Issue | High-voltage permits | 6
243 | 2025-09-02 | External Render | Hot / Dry | 0.75 | Large | 21 | Material Shortage | Local supplier backup | 6
244 | 2025-09-03 | Landscape Trees | Very Hot / Humid | 1 | Mega | 30 | Plant Disease | Expert horticulturalist | 5
245 | 2025-09-04 | Site Drilling | Very Hot / Dry | 1 | Infrastructure | 60 | Hard Rocks | Specialized drill bits | 14
246 | 2025-09-05 | Grid Connection | Hot / Dry | 1 | Infrastructure | 90 | Meter Delay | Early SEC coordination | 17
247 | 2025-09-06 | HVAC Ducting | Very Hot / Humid | 0.85 | Mega | 25 | Design Clash (BIM) | BIM Coordination | 3
248 | 2025-09-07 | Slab Pouring | Hot / Dry | 0.8 | Giga | 30 | Concrete Supply | Chilled water usage | 5
249 | 2025-09-08 | Pre-cast Walls | Very Hot / Dry | 0.9 | Giga | 45 | Normal | Factory-controlled env | 2
250 | 2025-09-09 | Concrete Curing | Hot / Dry | 0.95 | Large | 7 | Additive Delay | Accelerated curing agents | 3
251 | 2025-09-10 | Pre-cast Walls | Hot / Dry | 0.9 | Giga | 45 | Normal | Factory-controlled env | 4
252 | 2025-09-11 | Building Management | Hot / Dry | 1 | Mega | 30 | System Integration | BIM link-up | 8
253 | 2025-09-12 | Concrete Works | Very Hot / Dry | 1 | Giga | 25 | Material Batch | Quality control on-site | 6
254 | 2025-09-13 | Exterior Tiling | Very Hot / Humid | 0.7 | Medium | 15 | Adhesive Delay | Heat-resistant glue | 7
255 | 2025-09-14 | Swimming Pools | Hot / Dry | 0.9 | Large | 30 | Normal | Water testing | 5
256 | 2025-09-15 | Key Handover | Hot / Dry | 1 | Small | 5 | Admin Issues | Early document prep | 1
257 | 2025-09-16 | Water Insulation | Very Hot / Dry | 1 | Large | 12 | Normal | Surface drying machines | 4
258 | 2025-09-17 | Steel Erection | Hot / Dry | 0.75 | Mega | 40 | Normal | Night shift work | 4
259 | 2025-09-18 | Piling Works | Very Hot / Dry | 0.9 | Giga | 90 | Normal | Soil consolidation | 8
260 | 2025-09-19 | Elevator Shafts | Very Hot / Humid | 1 | Large | 40 | Customs Delay | Early shipping | 12
261 | 2025-09-20 | Concrete Works | Very Hot / Humid | 1 | Giga | 25 | Material Batch | Quality control on-site | 2
262 | 2025-09-21 | HVAC Testing | Hot / Dry | 0.85 | Large | 20 | Unit Failure | Spare parts on-site | 7
263 | 2025-09-22 | Final Finishing | Very Hot / Humid | 0.9 | Small | 20 | Normal | Air-conditioned site | 2
264 | 2025-09-23 | Smart Systems | Very Hot / Humid | 1 | Mega | 15 | Tech Setup Issue | Early software testing | 6
265 | 2025-09-24 | Solar Panel Install | Very Hot / Dry | 1 | Mega | 30 | Customs Delay | Early clearing | 13
266 | 2025-09-25 | Smart Systems | Hot / Dry | 1 | Giga | 60 | Sensor Delay | Direct air-freight | 13
267 | 2025-09-26 | Plastering | Very Hot / Dry | 0.8 | Large | 20 | Normal | Enclosed working area | 5
268 | 2025-09-27 | Basement Slab | Hot / Dry | 1 | Large | 20 | Additive Delay | Thermal blankets | 2
269 | 2025-09-28 | Steel Erection | Hot / Dry | 0.75 | Mega | 40 | Normal | Night shift work | 9
270 | 2025-09-29 | Steel Structure | Very Hot / Humid | 0.8 | Infrastructure | 45 | Steel Shortage | Early procurement | 12
271 | 2025-09-30 | Solar Panel Install | Hot / Dry | 1 | Mega | 30 | Customs Delay | Early clearing | 11
272 | 2025-10-01 | Roof Insulation | Warm / Clear | 0.9 | Small | 7 | Normal | Early morning shifts | 1
273 | 2025-10-02 | Data Center | Warm / Clear | 0.95 | Mega | 60 | Cooling Units | Factory FAT testing | 8
274 | 2025-10-03 | Pool Filtration | Warm / Windy | 1 | Small | 12 | Normal | System pre-test | 3
275 | 2025-10-04 | Main Substation | Warm / Clear | 1 | Giga | 120 | SEC Approval | Gov Liaison Officer | 22
276 | 2025-10-05 | Slab Pouring | Warm / Dusty | 0.8 | Giga | 30 | Concrete Supply | Chilled water usage | 5
277 | 2025-10-06 | Smart Systems | Warm / Windy | 1 | Giga | 60 | Sensor Delay | Direct air-freight | 9
278 | 2025-10-07 | Basement Slab | Warm / Windy | 1 | Large | 20 | Additive Delay | Thermal blankets | 5
279 | 2025-10-08 | Concrete Slab | Warm / Clear | 0.85 | Giga | 30 | Normal | Chilled water usage | 5
280 | 2025-10-09 | Exterior Tiling | Warm / Windy | 0.7 | Medium | 15 | Adhesive Delay | Heat-resistant glue | 7
281 | 2025-10-10 | Retaining Walls | Warm / Clear | 0.85 | Giga | 50 | Logistic Delay | Temporary site access | 15
282 | 2025-10-11 | Site Surveying | Warm / Dusty | 0.9 | Infrastructure | 15 | Equipment Error | Laser calibration | 1
283 | 2025-10-12 | HVAC Testing | Warm / Clear | 0.85 | Large | 20 | Unit Failure | Spare parts on-site | 8
284 | 2025-10-13 | Fire Sprinklers | Warm / Dusty | 0.95 | Mega | 35 | Normal | Pressure testing | 1
285 | 2025-10-14 | Handrail Install | Warm / Clear | 1 | Small | 7 | Normal | Local workshop | 3
286 | 2025-10-15 | Asphalt Paving | Warm / Windy | 0.85 | Infrastructure | 14 | Batch Plant Delay | Priority scheduling | 6
287 | 2025-10-16 | Glass Fitting | Warm / Dusty | 1 | Large | 20 | Broken Cargo | 10% extra buffer stock | 11
288 | 2025-10-17 | Window Glazing | Warm / Clear | 0.8 | Medium | 14 | Glass Breakage | Specialized storage | 6
289 | 2025-10-18 | Handrail Install | Warm / Dusty | 1 | Small | 7 | Normal | Local workshop | 0
290 | 2025-10-19 | Signaling Sys | Warm / Dusty | 0.85 | Infrastructure | 60 | Tech Delay | Government approval | 17
291 | 2025-10-20 | Foundations | Warm / Windy | 0.95 | Large | 14 | Normal | Soil stabilization | 5
292 | 2025-10-21 | HVAC Testing | Warm / Clear | 0.85 | Large | 20 | Unit Failure | Spare parts on-site | 11
293 | 2025-10-22 | Site Clearing | Warm / Clear | 0.8 | Small | 5 | Normal | Heavy machinery | 3
294 | 2025-10-23 | Concrete Slab | Warm / Dusty | 0.85 | Giga | 30 | Normal | Chilled water usage | 4
295 | 2025-10-24 | Final Inspection | Warm / Clear | 1 | Medium | 10 | Compliance Issue | Pre-audit check | 14
296 | 2025-10-25 | Infrastructure Pipes | Warm / Dusty | 0.95 | Infrastructure | 90 | Underground Utility | Utility mapping | 9
297 | 2025-10-26 | Substation Setup | Warm / Clear | 1 | Giga | 90 | Transformer Delay | Temporary power | 23
298 | 2025-10-27 | Solar Farm | Warm / Clear | 1 | Giga | 120 | Port Delay | Local storage buffer | 21
299 | 2025-10-28 | Landscaping | Warm / Windy | 1 | Medium | 30 | Plant Mortality | Winter protection | 3
300 | 2025-10-29 | Sound Systems | Warm / Windy | 1 | Medium | 10 | Normal | Calibration experts | 0
301 | 2025-10-30 | Data Center | Warm / Dusty | 0.95 | Mega | 60 | Cooling Units | Factory FAT testing | 11
302 | 2025-10-31 | Fire Sprinklers | Warm / Windy | 0.95 | Mega | 35 | Normal | Pressure testing | 1
303 | 2025-11-01 | False Ceilings | Warm / Dusty | 0.95 | Medium | 12 | Material Shortage | Alternative suppliers | 4
304 | 2025-11-02 | Swimming Pools | Warm / Dusty | 0.9 | Large | 30 | Normal | Water testing | 2
305 | 2025-11-03 | Site Compaction | Warm / Clear | 0.8 | Large | 10 | Normal | Moisture control | 7
306 | 2025-11-04 | Grid Connection | Warm / Clear | 1 | Infrastructure | 90 | Meter Delay | Early SEC coordination | 15
307 | 2025-11-05 | Concrete Works | Warm / Dusty | 1 | Giga | 25 | Material Batch | Quality control on-site | 4
308 | 2025-11-06 | Gas Systems | Warm / Windy | 0.85 | Large | 25 | Valve Delay | Safety valve backup | 10
309 | 2025-11-07 | Fire Sprinklers | Warm / Windy | 0.95 | Mega | 35 | Normal | Pressure testing | 0
310 | 2025-11-08 | Data Cabling | Warm / Clear | 0.9 | Large | 25 | Cable Shortage | Bulk ordering | 5
311 | 2025-11-09 | Gas Systems | Warm / Clear | 0.85 | Large | 25 | Valve Delay | Safety valve backup | 10
312 | 2025-11-10 | Grid Connection | Warm / Dusty | 1 | Infrastructure | 60 | SEC Approval | Gov Liaison support | 15
313 | 2025-11-11 | Exterior Tiling | Warm / Clear | 0.7 | Medium | 15 | Adhesive Delay | Heat-resistant glue | 8
314 | 2025-11-12 | Project Handover | Warm / Dusty | 1 | Giga | 30 | Admin Issues | Final Ministerial Sign-off | 19
315 | 2025-11-13 | Window Glazing | Warm / Dusty | 0.8 | Medium | 14 | Glass Breakage | Specialized storage | 5
316 | 2025-11-14 | External Cladding | Warm / Dusty | 0.75 | Large | 25 | Supply Shortage | Local sourcing | 7
317 | 2025-11-15 | Steel Structure | Warm / Windy | 0.8 | Infrastructure | 45 | Steel Shortage | Early procurement | 8
318 | 2025-11-16 | Wooden Works | Warm / Dusty | 0.85 | Medium | 15 | Humidity Issue | Climate-controlled storage | 6
319 | 2025-11-17 | Infrastructure Pipes | Warm / Dusty | 0.95 | Infrastructure | 90 | Underground Utility | Utility mapping | 8
320 | 2025-11-18 | Fire Fighting Sys | Warm / Windy | 1 | Large | 25 | Valve Shortage | Pre-ordering valves | 6
321 | 2025-11-19 | Fire Suppression | Warm / Dusty | 1 | Mega | 20 | Valve Delay | Pre-installation audit | 6
322 | 2025-11-20 | Electrical (Main) | Warm / Clear | 0.9 | Giga | 60 | Transformer Delay | Temporary generators | 17
323 | 2025-11-21 | Site Clearing | Warm / Dusty | 0.8 | Small | 5 | Normal | Heavy machinery | 6
324 | 2025-11-22 | Asphalt Paving | Warm / Clear | 0.85 | Infrastructure | 14 | Batch Plant Delay | Priority scheduling | 5
325 | 2025-11-23 | Swimming Pool | Warm / Clear | 0.7 | Small | 20 | Normal | Night shift tiling | 8
326 | 2025-11-24 | Concrete Pouring | Warm / Windy | 1 | Mega | 20 | Pump Failure | Backup pump on-site | 5
327 | 2025-11-25 | Fire Suppression | Warm / Clear | 1 | Mega | 20 | Valve Delay | Pre-installation audit | 4
328 | 2025-11-26 | Fire Sprinklers | Warm / Clear | 0.95 | Mega | 35 | Normal | Pressure testing | 3
329 | 2025-11-27 | Swimming Pools | Warm / Clear | 0.9 | Large | 30 | Normal | Water testing | 1
330 | 2025-11-28 | Foundations | Warm / Windy | 1 | Mega | 40 | Normal | Dewatering system | 4
331 | 2025-11-29 | Fire Fighting Sys | Warm / Clear | 1 | Large | 25 | Valve Shortage | Pre-ordering valves | 5
332 | 2025-11-30 | Slab Pouring | Warm / Clear | 0.8 | Giga | 30 | Concrete Supply | Chilled water usage | 2
333 | 2025-12-01 | Glass Fitting | Cool / Chance of Rain | 1 | Large | 20 | Broken Cargo | 10% extra buffer stock | 10
334 | 2025-12-02 | Piling Works | Cool / Clear | 0.9 | Giga | 90 | Normal | Soil consolidation | 9
335 | 2025-12-03 | Fire Alarm | Cool / Chance of Rain | 1 | Medium | 15 | Normal | Pre-testing circuits | 0
336 | 2025-12-04 | Smart Home Hub | Cool / Cloudy | 0.95 | Medium | 10 | Firmware Issue | Remote tech support | 3
337 | 2025-12-05 | Pre-cast Walls | Cool / Cloudy | 0.9 | Giga | 45 | Normal | Factory-controlled env | 6
338 | 2025-12-06 | Data Cabling | Cool / Cloudy | 0.9 | Large | 25 | Cable Shortage | Bulk ordering | 4
339 | 2025-12-07 | Handrail Install | Cool / Windy | 1 | Small | 7 | Normal | Local workshop | 0
340 | 2025-12-08 | HVAC Ducting | Cool / Clear | 0.85 | Mega | 25 | Design Clash (BIM) | BIM Coordination | 4
341 | 2025-12-09 | Excavation | Cool / Cloudy | 0.9 | Infrastructure | 20 | Normal | Drainage & slope prep | 5
342 | 2025-12-10 | Irrigation | Cool / Cloudy | 0.9 | Large | 25 | Pump Delay | Water truck support | 8
343 | 2025-12-11 | Data Cabling | Cool / Clear | 0.9 | Large | 25 | Cable Shortage | Bulk ordering | 5
344 | 2025-12-12 | Smart Systems | Cool / Windy | 1 | Mega | 15 | Tech Setup Issue | Early software testing | 10
345 | 2025-12-13 | Indoor Paint | Cool / Chance of Rain | 1 | Small | 10 | Normal | Air conditioning | 0
346 | 2025-12-14 | Landscape/Trees | Cool / Windy | 0.85 | Mega | 30 | Plant Mortality | Automated irrigation | 10
347 | 2025-12-15 | Fire Sprinklers | Cool / Windy | 0.95 | Mega | 35 | Normal | Pressure testing | 0
348 | 2025-12-16 | Marble Flooring | Cool / Windy | 0.8 | Medium | 20 | Logistic Delay | Direct factory shipping | 5
349 | 2025-12-17 | Roof Insulation | Cool / Chance of Rain | 0.9 | Small | 7 | Normal | Early morning shifts | 4
350 | 2025-12-18 | Fire Suppression | Cool / Chance of Rain | 1 | Mega | 20 | Valve Delay | Pre-installation audit | 8
351 | 2025-12-19 | Data Center | Cool / Cloudy | 0.95 | Mega | 60 | Cooling Units | Factory FAT testing | 10
352 | 2025-12-20 | Concrete Works | Cool / Chance of Rain | 1 | Giga | 25 | Material Batch | Quality control on-site | 5
353 | 2025-12-21 | Exterior Tiling | Cool / Clear | 0.7 | Medium | 15 | Adhesive Delay | Heat-resistant glue | 4
354 | 2025-12-22 | False Ceilings | Cool / Chance of Rain | 0.95 | Medium | 12 | Material Shortage | Alternative suppliers | 6
355 | 2025-12-23 | Data Center | Cool / Windy | 0.95 | Mega | 60 | Cooling Units | Factory FAT testing | 10
356 | 2025-12-24 | Electrical (Main) | Cool / Cloudy | 0.9 | Giga | 60 | Transformer Delay | Temporary generators | 15
357 | 2025-12-25 | Infrastructure Pipes | Cool / Chance of Rain | 0.95 | Infrastructure | 90 | Underground Utility | Utility mapping | 8
358 | 2025-12-26 | Soil Compaction | Cool / Cloudy | 0.85 | Infrastructure | 20 | Normal | Soil stabilization | 7
359 | 2025-12-27 | Infrastructure Pipes | Cool / Clear | 0.95 | Infrastructure | 90 | Underground Utility | Utility mapping | 12
360 | 2025-12-28 | Site Compaction | Cool / Clear | 0.8 | Large | 10 | Normal | Moisture control | 6
361 | 2025-12-29 | Site Surveying | Cool / Cloudy | 0.9 | Infrastructure | 15 | Equipment Error | Laser calibration | 3
362 | 2025-12-30 | Pre-cast Walls | Cool / Chance of Rain | 0.9 | Giga | 45 | Normal | Factory-controlled env | 3
363 | 2025-12-31 | Pool Filtration | Cool / Cloudy | 1 | Small | 12 | Normal | System pre-test | 0
364 | 2026-01-01 | Landscaping | Cool / Windy | 1 | Medium | 30 | Plant Mortality | Winter protection | 5
365 | 2026-01-02 | Slab Pouring | Cool / Cloudy | 0.8 | Giga | 30 | Concrete Supply | Chilled water usage | 7